## Slide 1: Instructions for facilitator
To prepare
Ask the course team to reflect on the project as a preparation for this meeting.
List of materials
N/a

## Slide 2
DARE is inspired by the Carpe Diem Design Approach by Gilly Salmon and adapted based on insights of (re)designing over 100 blended courses.
Except where otherwise noted this presentation is available under a Creative Commons Attribution 4.0 international license. Please attribute Delft University of Technology.

## Slide 3: Process Evaluation
Photo by John Schnobrich on Unsplash

## Slide 4: The 8 steps of DARE
Kick-Off
Blueprint
Storyboard
Prototypes
Planning
Development
Run
Evaluation

## Slide 5
Process evaluation is a moment
of reflection related to team
processes independent of content.

## Slide 6: Agenda
Note keeping
Acknowledgements
Process review
Focus & next steps

## Slide 7
Note keeping
1
Who will take notes?
Photo by Glenn Carstens-Peters on Unsplash

## Slide 8
Acknowledgements
2
Before we start
Photo by Antonio Janesky on Unsplash

## Slide 9: We acknowledge that
All team members gave it their best over the course of this project:
applying their skills competencies
making use of the available tools & resources
within the given context (time & availability)
Photo by Ken Suarez on Unsplash
Notes: The goal is to create a safe environment to share & evaluate and avoid pointing fingers.
This can be used as the premise to focus on the process.

## Slide 10
Process review
3
How did we collaborate?
Photo by Markus Winkler on Unsplash

## Slide 11: Retrospective
What did we do well?
What did we learn?
What should we do differently in the future?
What do we still not understand?
Photo by Jim Romero on Unsplash
Notes: It’s similar to the keep, change, create exercise but then focused on the process. Despite this only being 4 questions, an hour can easily be spent on these.
Potentially split focus on:
communication (tools/platform/style),
availability,
planning,
dependencies,
general dynamics

## Slide 12
Next steps
4
Focus & follow-up
Photo by Lindsay Henwood on Unsplash

## Slide 13: Next steps
Which improvements are we going to focus on?
Are we planning to collaborate again in the future?
Next meeting: ?

## Slide 14
Kick-Off
Blueprint
Storyboard
Prototypes
Planning
Development
Run
Evaluation
The 8 steps of DARE